## Project Phases
Phase | Timeline | Major Milestones / Deliverables
Phase 1 – Discovery & Requirements | Week 1–2 | Kick-off Meeting, Data Source Inventory, KPI Catalog Definition, Wireframes, Data Governance Requirements
Phase 2 – Data Architecture & Modeling | Week 3–6 | Data Model Blueprint, Dimensional Model, Relationship Matrix
Phase 3 – Dashboard Design & Development | Week 7–10 | Theme JSON, Report Pages, KPI Cards, Variance Visuals
Phase 4 – Testing & Validation | Week 11–12 | Data Accuracy Testing, Performance Optimization, UAT Sign-off
Phase 5 – Deployment & Training | Week 13–14 | Workspace Setup, Scheduled Refresh, User Training
Phase 6 – Post-Deployment & Continuous Improvement | Ongoing | Governance Review, Dashboard Enhancements, Feedback Loop

## Work Breakdown Structure
Task ID | Task Name | Duration | Responsible | Dependencies
1.1 | Kick-off and scope alignment | 2 days | PM / Sponsor | -
1.2 | Source data mapping | 3 days | Data Engineer | 1.1
2.1 | DimDate and DimSites creation | 4 days | Data Architect | 1.2
2.2 | Fact_Actuals_Keyed creation | 3 days | Data Engineer | 2.1
2.3 | Model validation and relationships | 3 days | Data Architect | 2.2
3.1 | Report wireframes (Overview, Voice) | 5 days | BI Developer | 2.3
3.2 | KPI DAX measure implementation | 4 days | BI Developer | 3.1
3.3 | Formatting and navigation design | 3 days | BI Developer | 3.2
4.1 | QA testing and UAT | 5 days | QA Lead | 3.3
5.1 | Deployment and workspace setup | 3 days | PM / BI Lead | 4.1
5.2 | End-user training and documentation | 2 days | PM / BI Lead | 5.1
6.1 | Post-deployment review | Ongoing | BI Team | 5.2
6.2 | Enhancement planning | Ongoing | BI Team | 6.1

## Risks & Mitigation
Risk | Impact | Mitigation
Data latency from EVA | High | Schedule incremental refresh and pre-aggregations
KPI definition misalignment | Medium | Conduct early validation workshops
Visual performance lag | High | Use optimized DAX, aggregation tables, and performance tuning
User adoption gap | Medium | Provide continuous user engagement and training
Inconsistent data governance | High | Implement metadata documentation and quality checks