# Power BI Project Plan

## 1. Project Overview

1.1 Purpose
To develop an integrated Power BI analytics framework for executive decision making across all commercial business units.

1.2 Background
EVA is sole data source of from which all the datasets will be fed into power bi.

1.3 Scope

- Included: BI data modeling, ETL integration, KPI design, dashboard development, deployment, and governance setup.

- Excluded: Source system redesign, API development, or non-MTN subsidiaries (unless explicitly stated).

1.4 Objectives

- Establish a robust Power BI semantic model (Actuals vs Budget, RGS, ADS, MoMo, etc.)

- Deliver MTN-branded dashboards for CEO, CBU, EBU, Fintech, and S&D.

- Implement governance (refresh schedules, access control, data lineage).

- Train local BI and CVM teams.

## 2. Governance and Stakeholders

| Role | Name / Department | Responsibility |
| --- | --- | --- |
| Executive Sponsor | CEO / CMO | Approves deliverables |
| Project Lead | BI & Analytics Manager | Coordination and milestone validation |
| Data Architect | Consultant | Model design and schema |
| Power BI Developer | Consultant | PBIX build and optimization |
| Data Engineer | EVA Team | ETL and data quality |
| QA Lead | PMO | Testing and acceptance |

## 3. Project Phases and Milestones

### Phase 1 – Discovery & Requirements (Week 1–2)

Milestones

- ✅ Kick-off Meeting

- ✅ Data Source Inventory

- ✅ KPI Catalog Definition

- ✅ Report Wireframes (Executive, Voice, Data, MoMo, S&D)

- ✅ Data Governance Requirements

Tasks

- Conduct stakeholder workshops

- Define business questions & KPI hierarchies

- Identify data pain points (granularity, refresh latency, orphan records)

- Define security roles (CEO view, CMO view, analyst view)

Deliverables

- Requirements Specification Document

- KPI Dictionary / Metadata sheet

- Wireframes and Storyboards

### Phase 2 – Data Architecture & Modeling (Week 3–6)

Milestones

- Data Model Blueprint Approved

- Dimensional Model Implemented (Fact_Actuals_Keyed, Fact_Budget_Keyed, DimDate, DimSites, DimKpis, etc.)

- Relationship Matrix Completed

Tasks

- Design star schema

- Map staging tables (stg_Facts_Actuals, stg_Facts_Budget) to final tables

- Implement surrogate keys and hierarchies

- Define and validate calculated measures (Actuals, Budget, Δ%, MTD, YTD, etc.)

- Document lineage and dependencies

Deliverables

- Data Model Documentation (ERD + field catalog)

- Power Query transformation scripts

- Model governance sheet

### Phase 3 – Dashboard Design & Development (Week 7–10)

Milestones

- MTN Theme JSON finalized

- Report Pages (Overview, Voice, Data, MoMo, S&D) built

- KPI Cards & Variance visuals validated

Tasks

- Apply MTN design standards (font, colors, iconography)

- Develop DAX measures (Day, WoW, MoM, YTD comparisons)

- Implement dynamic slicers (Geo, Segment, Call Direction, Date)

- Optimize visuals (multi-row cards, matrix tables, navigation buttons)

- Add tooltips and narrative summaries

Deliverables

- PBIX files for each domain

- Design System / UI specification

- Screenshot mockups for management validation

### Phase 4 – Testing & Validation (Week 11–12)

Milestones

- Data accuracy tested

- Performance optimization complete

- User Acceptance Test signed off

Tasks

- Validate KPI values vs EVA warehouse

- Conduct performance benchmarking (model size, refresh duration, DAX performance)

- Implement security and RLS

- Conduct user feedback sessions

Deliverables

- Test case matrix

- UAT sign-off sheet

- Performance optimization report

### Phase 5 – Deployment & Training (Week 13–14)

Milestones

- Workspace structure created (Dev, QA, Prod)

- Scheduled refresh configured (Fabric Premium)

- User training delivered

Tasks

- Publish reports to Power BI Service

- Assign security roles and permissions

- Configure dataset refresh and gateway connections

- Develop user manual and training slides

Deliverables

- Power BI Service workspace setup document

- Refresh and Access governance plan

- End-user training materials

### Phase 6 – Post-Deployment & Continuous Improvement (Ongoing)

Milestones

- BI Governance Review

- Dashboard Enhancement Roadmap

Tasks

- Monitor adoption metrics (usage logs, refresh success)

- Collect feedback and plan next iteration (e.g., Predictive CVM dashboard, Fintech integrations)

- Update data dictionary and metadata

Deliverables

- Adoption report

- Continuous improvement log

- Version control and release notes

## 4. Detailed Work Breakdown Structure (WBS)

| # | Task | Duration | Responsible | Dependencies |
| --- | --- | --- | --- | --- |
| 1.1 | Kick-off and scope alignment | 2 days | PM / Sponsor | – |
| 1.2 | Source data mapping | 3 days | Data Engineer | 1.1 |
| 2.1 | DimDate and DimSites creation | 4 days | Data Architect | 1.2 |
| 2.2 | Fact_Actuals_Keyed creation | 3 days | Data Engineer | 2.1 |
| 3.1 | Report wireframes (Overview, Voice) | 5 days | BI Developer | 2.2 |
| 3.2 | KPI DAX measure implementation | 4 days | BI Developer | 3.1 |
| 4.1 | QA and UAT | 5 days | QA Lead | 3.2 |
| 5.1 | Deployment and training | 3 days | PM / BI Lead | 4.1 |

## 5. Risks & Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Data latency from EVA | High | Schedule incremental refresh and pre-aggregations |
| KPI definition misalignment | Medium | Early validation workshops |
| Visual performance lag | High | Use optimized DAX and aggregated tables |
| User adoption gap | Medium | Train and build executive champions |

## 6. Success Metrics

- Dashboard refresh < 5 minutes

- 100% KPI reconciliation with source system

- 80% stakeholder satisfaction in UAT

- 60% monthly active user rate after launch

## 7. Appendices

- Appendix A: KPI Catalog

- Appendix B: ERD Diagram

- Appendix C: Governance Policy

- Appendix D: Change Request Log

Would you like me to generate this as a downloadable .docx version (formatted with MTN-style headers, table formatting, and editable milestone sections)? I can do that next.